## Python Logic Tests
GEEK Streaming Support: Python Logic Test Plan
Source notebook | See python/StreamingChatBotAI-Project.ipynb in this repository.
Run one row at a time in Colab. Enter the four input values shown, copy the final message into Actual Final Result, and select a status.
Tests TC-033 through TC-040 check invalid or differently formatted input. A failure there can be documented as a code improvement in the case study.
Total Tests | Pass | Fail | Blocked | Not Tested | Completion
40 | 37 | 3 | 0 | 0 | 100%
Test ID | Test Type | Category | Symptom / Scenario | Main Menu Input | Symptom Input | Diagnostic Answer | Resolved Answer | Expected Final Result | Actual Final Result | Status | Notes / Fix Needed | Retest Status | Date Tested
TC-001 | Valid path | Power | Won't turn on | 1 | 1 | yes | yes | Awesome! Glad it's working. | Awesome! Glad it's working. | Pass | Status light visible; input or HDMI change resolves issue. | Not Needed | 2026-09-28
TC-002 | Valid path | Power | Won't turn on | 1 | 1 | yes | no | Escalation: Creating a ticket and connecting you to a Hardware Specialist for further diagnostics... | Escalation: Creating a ticket and connecting you to a Hardware Specialist for further diagnostics... | Pass | Status light visible; input or HDMI change does not resolve issue. | Not Needed | 2026-09-28
TC-003 | Valid path | Power | Won't turn on | 1 | 1 | no | yes | Great! You are good to go. | Great! You are good to go. | Pass | No status light; securing the power cable resolves issue. | Not Needed | 2026-09-28
TC-004 | Valid path | Power | Won't turn on | 1 | 1 | no | no | Escalation: Creating a hardware replacement ticket for your power adapter... | Escalation: Creating a hardware replacement ticket for your power adapter... | Pass | No status light; securing the power cable does not resolve issue. | Not Needed | 2026-09-28
TC-005 | Valid path | Power | Keeps restarting | 1 | 2 | no | yes | Perfect! Direct wall power solves a lot of issues. | Perfect! Direct wall power solves a lot of issues. | Pass | Device was not connected directly to the wall; moving it resolves issue. | Not Needed | 2026-09-28
TC-006 | Valid path | Power | Keeps restarting | 1 | 2 | no | no | Escalation: Creating a ticket and transferring to Tier 2 Support to check for a system boot loop... | Escalation: Creating a ticket and transferring to Tier 2 Support to check for a system boot loop... | Pass | Moving the device to wall power does not resolve restarting. | Not Needed | 2026-09-28
TC-007 | Valid path | Power | Keeps restarting | 1 | 2 | yes | yes | Excellent! Enjoy your streaming. | Excellent! Enjoy your streaming. | Pass | Device was already connected to wall power; power cycle resolves issue. | Not Needed | 2026-09-28
TC-008 | Valid path | Power | Keeps restarting | 1 | 2 | yes | no | Escalation: Creating ticket and connecting to Tier 2 Support to perform a factory reset... | Escalation: Creating ticket and connecting to Tier 2 Support to perform a factory reset... | Pass | Device was already connected to wall power; power cycle does not resolve issue. | Not Needed | 2026-09-28
TC-009 | Valid path | Connection | No Internet | 2 | 1 | no | yes | Awesome! We're back online | Awesome! We're back online | Pass | Wi-Fi is down on other devices; router restart resolves issue. | Not Needed | 2026-09-28
TC-010 | Valid path | Connection | No Internet | 2 | 1 | no | no | Escalation: We recommend contacting your Internet Service Provider. | Escalation: We recommend contacting your Internet Service Provider. | Pass | Wi-Fi is down on other devices; router restart does not resolve issue. | Not Needed | 2026-09-28
TC-011 | Valid path | Connection | No Internet | 2 | 1 | yes | yes | Perfect! Network settings refreshed successfully. | Perfect! Network settings refreshed successfully. | Pass | Wi-Fi works elsewhere; reconnecting the streaming device resolves issue. | Not Needed | 2026-09-28
TC-012 | Valid path | Connection | No Internet | 2 | 1 | yes | no | Escalation: Creating a ticket and routing you to a Network Specialist to check your device's MAC address... | Escalation: Creating a ticket and routing you to a Network Specialist to check your device's MAC address... | Pass | Wi-Fi works elsewhere; reconnecting the streaming device does not resolve issue. | Not Needed | 2026-09-28
TC-013 | Valid path | Connection | Buffering | 2 | 2 | yes | yes | Wonderful! Clearing the line of sight always helps. | Wonderful! Clearing the line of sight always helps. | Pass | Device is obstructed; moving it to an open area resolves buffering. | Not Needed | 2026-09-28
TC-014 | Valid path | Connection | Buffering | 2 | 2 | yes | no | Escalation: Creating a ticket and routing to Tier 2 Support to discuss a wi-fi range extender or ethernet adapter... | Escalation: Creating a ticket and routing to Tier 2 Support to discuss a wi-fi range extender or ethernet adapter... | Pass | Device is obstructed; moving it does not resolve buffering. | Not Needed | 2026-09-28
TC-015 | Valid path | Connection | Buffering | 2 | 2 | no | yes | Awesome! Back to smooth streaming. | Awesome! Back to smooth streaming. | Pass | Device is unobstructed; settings change or restart resolves buffering. | Not Needed | 2026-09-28
TC-016 | Valid path | Connection | Buffering | 2 | 2 | no | no | Escalation: Creating ticket and connecting you to a Streaming Media Specialist now... | Escalation: Creating ticket and connecting you to a Streaming Media Specialist now... | Pass | Device is unobstructed; settings change or restart does not resolve buffering. | Not Needed | 2026-09-28
TC-017 | Valid path | Audio/Video | Black or blank screen | 3 | 1 | no | yes | Perfect! A loose HDMI connection is super common. | Perfect! A loose HDMI connection is super common. | Pass | HDMI was not secure or alternate port not tried; securing it resolves issue. | Not Needed | 2026-09-28
TC-018 | Valid path | Audio/Video | Black or blank screen | 3 | 1 | no | no | Escalation: Creating a ticket and connecting you to our Hardware Team for deeper troubleshooting... | Escalation: Creating a ticket and connecting you to our Hardware Team for deeper troubleshooting... | Pass | Securing or swapping the HDMI port does not resolve issue. | Not Needed | 2026-09-28
TC-019 | Valid path | Audio/Video | Black or blank screen | 3 | 1 | yes | yes | Awesome! Glad to see your screen is back! | Awesome! Glad to see your screen is back! | Pass | HDMI was secure; changing cable or input resolves issue. | Not Needed | 2026-09-28
TC-020 | Valid path | Audio/Video | Black or blank screen | 3 | 1 | yes | no | Escalation: Creating a ticket and connecting you to our Hardware Team for video output failure... | Escalation: Creating a ticket and connecting you to our Hardware Team for video output failure... | Pass | Changing the HDMI cable or TV input does not resolve issue. | Not Needed | 2026-09-28
TC-021 | Valid path | Audio/Video | No sound | 3 | 2 | yes | yes | Great! Simple fixes are the best fixes. | Great! Simple fixes are the best fixes. | Pass | TV or soundbar was muted or low; correcting volume resolves issue. | Not Needed | 2026-09-28
TC-022 | Valid path | Audio/Video | No sound | 3 | 2 | yes | no | Escalation: Creating a ticket and getting you connected to our Hardware Team... | Escalation: Creating a ticket and getting you connected to our Hardware Team... | Pass | Correcting mute or volume does not resolve sound issue. | Not Needed | 2026-09-28
TC-023 | Valid path | Audio/Video | No sound | 3 | 2 | no | yes | Fantastic! Rock & Roll! | Fantastic! Rock & Roll! | Pass | Volume was not the issue; changing audio output resolves sound issue. | Not Needed | 2026-09-28
TC-024 | Valid path | Audio/Video | No sound | 3 | 2 | no | no | Escalation: Creating ticket and routing you to Tier 2 Support for audio hardware configuration... | Escalation: Creating ticket and routing you to Tier 2 Support for audio hardware configuration... | Pass | Changing audio output does not resolve sound issue. | Not Needed | 2026-09-28
TC-025 | Valid path | Remote | Unresponsive remote | 4 | 1 | no | yes | Awesome! Brand new batteries do the trick most of the time. | Awesome! Brand new batteries do the trick most of the time. | Pass | Batteries were not freshly replaced; new batteries resolve issue. | Not Needed | 2026-09-28
TC-026 | Valid path | Remote | Unresponsive remote | 4 | 1 | no | no | Escalation: Creating a ticket and connecting you to our Replacement Team to order a new remote... | Escalation: Creating a ticket and connecting you to our Replacement Team to order a new remote... | Pass | New batteries do not resolve remote responsiveness. | Not Needed | 2026-09-28
TC-027 | Valid path | Remote | Unresponsive remote | 4 | 1 | yes | yes | Perfect! Your remote is re-paired and ready. | Perfect! Your remote is re-paired and ready. | Pass | Batteries were new; forcing a re-pair resolves issue. | Not Needed | 2026-09-28
TC-028 | Valid path | Remote | Unresponsive remote | 4 | 1 | yes | no | Escalation: Creating a ticket and routing to Hardware Tech to check for a faulty IR/Bluetooth receiver on the device. | Escalation: Creating a ticket and routing to Hardware Tech to check for a faulty IR/Bluetooth receiver on the device. | Pass | Forcing a re-pair does not resolve issue. | Not Needed | 2026-09-28
TC-029 | Valid path | Remote | Voice control | 4 | 2 | no | yes | Great! Voice features are officially online. | Great! Voice features are officially online. | Pass | Account or internet was unavailable; signing in or reconnecting resolves issue. | Not Needed | 2026-09-28
TC-030 | Valid path | Remote | Voice control | 4 | 2 | no | no | Escalation: Creating a ticket and connecting you to Account Services to verify your profile settings... | Escalation: Creating a ticket and connecting you to Account Services to verify your profile settings... | Pass | Signing in or reconnecting does not resolve voice control. | Not Needed | 2026-09-28
TC-031 | Valid path | Remote | Voice control | 4 | 2 | yes | yes | Fantastic! Your microphone is working flawlessly now. | Fantastic! Your microphone is working flawlessly now. | Pass | Account and internet are valid; unpairing and re-pairing resolves issue. | Not Needed | 2026-09-28
TC-032 | Valid path | Remote | Voice control | 4 | 2 | yes | no | Escalating: Creating a ticket and transferring to Tier 2 Support to check for a corrupted update... | Escalating: Creating a ticket and transferring to Tier 2 Support to check for a corrupted update... | Pass | Unpairing and re-pairing does not resolve voice control. | Not Needed | 2026-09-28
TC-033 | Invalid input | Main menu | Out-of-range selection | 5 |  |  |  | Invalid choice. Please enter a number between 1 and 4. | Invalid choice. Please enter a number between 1 and 4. An exception has occurred, use %tb to see the full traceback. SystemExit /usr/local/lib/python3.13/dist-packages/IPython/core/interactiveshell.py:3561: UserWarning: To exit: use 'exit', 'quit', or Ctrl-D. warn("To exit: use 'exit', 'quit', or Ctrl-D.", stacklevel=1) | Pass | Verify the invalid choice message appears and the program exits. | Not Needed | 2026-09-28
TC-034 | Robustness | Main menu | Extra spaces | 1 | 1 | yes | yes | The program should trim spaces and route to Power. | Invalid choice. Please enter a number between 1 and 4. plus the SystemExit notice | Fail | Retest passed after adding .strip() to the main-menu input so extra spaces are removed before routing. | Pass | 2026-09-28
TC-035 | Invalid input | Power | Invalid symptom | 1 | 3 |  |  | Invalid choice for power troubleshooting. Please restart. | Invalid choice for power troubleshooting. Please restart. | Pass | Confirm the program displays the message and ends. | Not Needed | 2026-09-28
TC-036 | Invalid input | Connection | Invalid symptom | 2 | 3 |  |  | Invalid option. Redirecting you back to the main network settings menu. | Invalid option. Redirecting you back to the main network settings menu. | Pass | Confirm whether it actually redirects or only prints the message and ends. | Not Needed | 2026-09-28
TC-037 | Invalid input | Audio/Video | Invalid symptom | 3 | 3 |  |  | Invalid option. Redirecting you back to the main audio/video menu. | Invalid option. Redirecting you back to the main audio/video menu. | Pass | Confirm whether it actually redirects or only prints the message and ends. | Not Needed | 2026-09-28
TC-038 | Invalid input | Remote | Invalid symptom | 4 | 3 |  |  | Invalid option. Redirecting you back to the main remote menu. | Invalid option. Redirecting you back to the main remote menu. | Pass | Confirm whether it actually redirects or only prints the message and ends. | Not Needed | 2026-09-28
TC-039 | Robustness | Power | Uppercase yes | 1 | 1 | YES | yes | The program should interpret YES as yes and follow the status-light-visible path. | Great! You are good to go. | Fail | Retest passed after get_yes_no() normalized the response with .strip().lower(), allowing uppercase YES. | Pass | 2026-09-28
TC-040 | Robustness | Connection | Invalid resolved response | 2 | 2 | no | maybe | The program should reject the response and ask for yes or no again. | Awesome! Back to smooth streaming. | Fail | Retest passed after get_yes_no() rejected invalid responses and repeated the prompt until yes or no was entered. | Pass | 2026-09-28

## Flowchart Validation
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GEEK Streaming Support: Flowchart Validation Checklist
Use this tab to review the original Version 1 flowcharts against the Python notebook. Mark each item after visually tracing the chart.
This is a validation review, not a redesign. Record corrections in Notes and use the Defect & Retest Log when follow-up is required.
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Checks | Pass | Needs Update | Not Reviewed | 0 | 0 | 0 | 0
28 | 28 | 0 | 0 | 0 | 0 | 0 | 0
Check ID | Scope | Validation Check | Expected Standard | Status | Evidence / Location | Notes | Review Date
FC-001 | All charts | Four category flowcharts are included | Power, Connection, Audio/Video, and Remote charts are present. | Pass | All four category charts | 0 | 2026-09-29
FC-002 | All charts | Each chart clearly identifies its category | The title or starting decision names the correct category. | Pass | All four category charts | 0 | 2026-09-29
FC-003 | All charts | Each category contains two issue branches | Both issue options shown in the Python notebook appear. | Pass | All four category charts | 0 | 2026-09-29
FC-004 | All charts | Diagnostic decisions show both Yes and No routes | Each diagnostic question visibly branches in both directions. | Pass | All four category charts | 0 | 2026-09-29
FC-005 | All charts | Every diagnostic route leads to a troubleshooting action | No Yes or No branch stops before an action. | Pass | All four category charts | 0 | 2026-09-29
FC-006 | All charts | Every troubleshooting action leads to a resolution check | Each action is followed by a question confirming whether the issue was fixed. | Pass | All four category charts | 0 | 2026-09-29
FC-007 | All charts | Every resolution check has success and escalation routes | Yes reaches success and No reaches escalation. | Pass | All four category charts | 0 | 2026-09-29
FC-008 | All charts | Success and escalation endings are visually distinct | Outcome colors and labels make the ending immediately clear. | Pass | All four category charts | 0 | 2026-09-29
FC-009 | All charts | No nodes or arrows are disconnected | Every shape belongs to a complete start-to-finish route. | Pass | All four category charts | 0 | 2026-09-29
FC-010 | All charts | Arrow labels are readable and correctly positioned | Yes and No labels do not overlap arrows, shapes, or other text. | Pass | All four category charts | 0 | 2026-09-29
FC-011 | All charts | Spelling, capitalization, and terminology are consistent | Repeated terms use the same wording throughout. | Pass | All four category charts | 0 | 2026-09-29
FC-012 | All charts | All 32 valid paths can be traced | Each chart supports 8 complete routes: 4 diagnostic/fix routes ending in success or escalation. | Pass | All four category charts | 0 | 2026-09-29
FC-013 | Power | Issue branches match the notebook | Won't Turn On and Keeps Restarting are both included. | Pass | Power-Flow.png | 0 | 2026-09-29
FC-014 | Power | Diagnostic questions match the notebook | Status-light and direct-wall-power questions are represented correctly. | Pass | Power-Flow.png | 0 | 2026-09-29
FC-015 | Power | Troubleshooting actions match the notebook | HDMI/input, cable, wall-outlet, and 60-second power-cycle steps are present. | Pass | Power-Flow.png | 0 | 2026-09-29
FC-016 | Power | Power outcomes are complete | Four success routes and four escalation routes can be traced. | Pass | Power-Flow.png | 0 | 2026-09-29
FC-017 | Connection | Issue branches match the notebook | No Internet Error and Buffering are both included. | Pass | Connection-Flow.png | 0 | 2026-09-29
FC-018 | Connection | Diagnostic questions match the notebook | Other-device connectivity and device-placement questions are represented correctly. | Pass | Connection-Flow.png | 0 | 2026-09-29
FC-019 | Connection | Troubleshooting actions match the notebook | Router restart, Wi-Fi reconnect, relocation, and settings/restart steps are present. | Pass | Connection-Flow.png | 0 | 2026-09-29
FC-020 | Connection | Connection outcomes are complete | Four success routes and four escalation routes can be traced. | Pass | Connection-Flow.png | 0 | 2026-09-29
FC-021 | Audio/Video | Issue branches match the notebook | Black/Blank Screen and No Sound are both included. | Pass | Audio.Video-Flow.png | 0 | 2026-09-29
FC-022 | Audio/Video | Diagnostic questions match the notebook | HDMI connection and mute/volume questions are represented correctly. | Pass | Audio.Video-Flow.png | 0 | 2026-09-29
FC-023 | Audio/Video | Troubleshooting actions match the notebook | HDMI port/cable, input source, volume, and audio-output steps are present. | Pass | Audio.Video-Flow.png | 0 | 2026-09-29
FC-024 | Audio/Video | Audio/Video outcomes are complete | Four success routes and four escalation routes can be traced. | Pass | Audio.Video-Flow.png | 0 | 2026-09-29
FC-025 | Remote | Issue branches match the notebook | Remote Unresponsive and Voice Control Issues are both included. | Pass | Remote-Flow.png | 0 | 2026-09-29
FC-026 | Remote | Diagnostic questions match the notebook | Fresh-battery and account/internet questions are represented correctly. | Pass | Remote-Flow.png | 0 | 2026-09-29
FC-027 | Remote | Troubleshooting actions match the notebook | Battery replacement, re-pairing, sign-in, and full unpair/re-pair steps are present. | Pass | Remote-Flow.png | 0 | 2026-09-29
FC-028 | Remote | Remote outcomes are complete | Four success routes and four escalation routes can be traced. | Pass | Remote-Flow.png | 0 | 2026-09-29

## Landbot UAT
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GEEK Streaming Support: Landbot User Acceptance Testing
Run each test in the published Landbot. Record what happened, choose a status, and add a timestamp or screenshot reference when useful.
This log covers all core routes and shared features. The screen recording only needs representative tests, not every row.
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Tests | Pass | Fail | Blocked | Not Tested | Completion | 0 | 0 | 0 | 0 | 0
40 | 40 | 0 | 0 | 0 | 100% | 0 | 0 | 0 | 0 | 0
Test ID | Test Area | Category | Scenario / Route | User Selections / Action | Expected Result | Actual Result | Status | Evidence / Timestamp | Notes / Fix Needed | Date Tested
LB-001 | Core routing | Power | Won't turn on | Status light visible? Yes; complete: Switch TV input / check HDMI connection; resolved? Yes | Correct success message appears, then the More Help prompt. | Correct success message appears, followed by the More Help prompt. | Pass | 9:51 | 0 | 2026-09-29
LB-002 | Core routing | Power | Won't turn on | Status light visible? Yes; complete: Switch TV input / check HDMI connection; resolved? No | Correct unresolved message appears and the support-request form opens. | Correct unresolved message appears followed by the support-request form opens. | Pass | 9:54 | 0 | 2026-09-29
LB-003 | Core routing | Power | Won't turn on | Status light visible? No; complete: Secure power cable at wall and device; resolved? Yes | Correct success message appears, then the More Help prompt. | Correct success message appears, followed by the More Help prompt. | Pass | 9:56 | 0 | 2026-09-29
LB-004 | Core routing | Power | Won't turn on | Status light visible? No; complete: Secure power cable at wall and device; resolved? No | Correct unresolved message appears and the support-request form opens. | Correct unresolved message appears followed by the support-request form opens. | Pass | 9:57 | 0 | 2026-09-29
LB-005 | Core routing | Power | Keeps restarting | Plugged directly into a wall outlet? Yes; complete: Unplug for 60 seconds and reconnect; resolved? Yes | Correct success message appears, then the More Help prompt. | Correct success message appears, followed by the More Help prompt. | Pass | 9:58 | 0 | 2026-09-29
LB-006 | Core routing | Power | Keeps restarting | Plugged directly into a wall outlet? Yes; complete: Unplug for 60 seconds and reconnect; resolved? No | Correct unresolved message appears and the support-request form opens. | Correct unresolved message appears followed by the support-request form opens. | Pass | 9:59 | 0 | 2026-09-29
LB-007 | Core routing | Power | Keeps restarting | Plugged directly into a wall outlet? No; complete: Move power from TV USB to wall outlet; resolved? Yes | Correct success message appears, then the More Help prompt. | Correct success message appears, followed by the More Help prompt. | Pass | 10:08 | 0 | 2026-09-29
LB-008 | Core routing | Power | Keeps restarting | Plugged directly into a wall outlet? No; complete: Move power from TV USB to wall outlet; resolved? No | Correct unresolved message appears and the support-request form opens. | Correct unresolved message appears followed by the support-request form opens. | Pass | 10:09 | 0 | 2026-09-29
LB-009 | Core routing | Connection | No internet error | Wi-Fi working on other devices? Yes; complete: Forget and reconnect to Wi-Fi; resolved? Yes | Correct success message appears, then the More Help prompt. | Correct success message appears, followed by the More Help prompt. | Pass | 10:24 | 0 | 2026-09-29
LB-010 | Core routing | Connection | No internet error | Wi-Fi working on other devices? Yes; complete: Forget and reconnect to Wi-Fi; resolved? No | Correct unresolved message appears and the support-request form opens. | Correct unresolved message appears followed by the support-request form opens. | Pass | 10:25 | 0 | 2026-09-29
LB-011 | Core routing | Connection | No internet error | Wi-Fi working on other devices? No; complete: Restart router for 30 seconds; resolved? Yes | Correct success message appears, then the More Help prompt. | Correct success message appears, followed by the More Help prompt. | Pass | 10:27 | 0 | 2026-09-29
LB-012 | Core routing | Connection | No internet error | Wi-Fi working on other devices? No; complete: Restart router for 30 seconds; resolved? No | Correct unresolved message appears and the support-request form opens. | Correct unresolved message appears followed by the support-request form opens. | Pass | 10:28 | 0 | 2026-09-29
LB-013 | Core routing | Connection | Buffering | Device hidden or behind a heavy TV? Yes; complete: Move device to an open area; resolved? Yes | Correct success message appears, then the More Help prompt. | Correct success message appears, followed by the More Help prompt. | Pass | 10:34 | 0 | 2026-09-29
LB-014 | Core routing | Connection | Buffering | Device hidden or behind a heavy TV? Yes; complete: Move device to an open area; resolved? No | Correct unresolved message appears and the support-request form opens. | Correct unresolved message appears followed by the support-request form opens. | Pass | 10:35 | 0 | 2026-09-29
LB-015 | Core routing | Connection | Buffering | Device hidden or behind a heavy TV? No; complete: Lower video quality / restart device; resolved? Yes | Correct success message appears, then the More Help prompt. | Correct success message appears, followed by the More Help prompt. | Pass | 10:40 | 0 | 2026-09-29
LB-016 | Core routing | Connection | Buffering | Device hidden or behind a heavy TV? No; complete: Lower video quality / restart device; resolved? No | Correct unresolved message appears and the support-request form opens. | Correct unresolved message appears followed by the support-request form opens. | Pass | 10:41 | 0 | 2026-09-29
LB-017 | Core routing | Audio/Video | Black or blank screen | HDMI secured or another port tried? Yes; complete: Try a different HDMI cable and input; resolved? Yes | Correct success message appears, then the More Help prompt. | Correct success message appears, followed by the More Help prompt. | Pass | 21:12 | 0 | 2026-09-29
LB-018 | Core routing | Audio/Video | Black or blank screen | HDMI secured or another port tried? Yes; complete: Try a different HDMI cable and input; resolved? No | Correct unresolved message appears and the support-request form opens. | Correct unresolved message appears followed by the support-request form opens. | Pass | 21:13 | 0 | 2026-09-29
LB-019 | Core routing | Audio/Video | Black or blank screen | HDMI secured or another port tried? No; complete: Secure HDMI and try another port; resolved? Yes | Correct success message appears, then the More Help prompt. | Correct success message appears, followed by the More Help prompt. | Pass | 21:14 | 0 | 2026-09-29
LB-020 | Core routing | Audio/Video | Black or blank screen | HDMI secured or another port tried? No; complete: Secure HDMI and try another port; resolved? No | Correct unresolved message appears and the support-request form opens. | Correct unresolved message appears followed by the support-request form opens. | Pass | 21:15 | 0 | 2026-09-29
LB-021 | Core routing | Audio/Video | No sound | TV/soundbar muted or volume below 5? Yes; complete: Unmute and raise volume to 15; resolved? Yes | Correct success message appears, then the More Help prompt. | Correct success message appears, followed by the More Help prompt. | Pass | 21:16 | 0 | 2026-09-29
LB-022 | Core routing | Audio/Video | No sound | TV/soundbar muted or volume below 5? Yes; complete: Unmute and raise volume to 15; resolved? No | Correct unresolved message appears and the support-request form opens. | Correct unresolved message appears followed by the support-request form opens. | Pass | 21:17 | 0 | 2026-09-29
LB-023 | Core routing | Audio/Video | No sound | TV/soundbar muted or volume below 5? No; complete: Change audio output to Stereo or Auto; resolved? Yes | Correct success message appears, then the More Help prompt. | Correct success message appears, followed by the More Help prompt. | Pass | 21:18 | 0 | 2026-09-29
LB-024 | Core routing | Audio/Video | No sound | TV/soundbar muted or volume below 5? No; complete: Change audio output to Stereo or Auto; resolved? No | Correct unresolved message appears and the support-request form opens. | Correct unresolved message appears followed by the support-request form opens. | Pass | 21:19 | 0 | 2026-09-29
LB-025 | Core routing | Remote | Remote unresponsive | Fresh batteries installed? Yes; complete: Force re-pair near the streaming device; resolved? Yes | Correct success message appears, then the More Help prompt. | Correct success message appears, followed by the More Help prompt. | Pass | 21:20 | 0 | 2026-09-29
LB-026 | Core routing | Remote | Remote unresponsive | Fresh batteries installed? Yes; complete: Force re-pair near the streaming device; resolved? No | Correct unresolved message appears and the support-request form opens. | Correct unresolved message appears followed by the support-request form opens. | Pass | 21:20 | 0 | 2026-09-29
LB-027 | Core routing | Remote | Remote unresponsive | Fresh batteries installed? No; complete: Replace batteries and drain leftover power; resolved? Yes | Correct success message appears, then the More Help prompt. | Correct success message appears, followed by the More Help prompt. | Pass | 21:21 | 0 | 2026-09-29
LB-028 | Core routing | Remote | Remote unresponsive | Fresh batteries installed? No; complete: Replace batteries and drain leftover power; resolved? No | Correct unresolved message appears and the support-request form opens. | Correct unresolved message appears followed by the support-request form opens. | Pass | 21:22 | 0 | 2026-09-29
LB-029 | Core routing | Remote | Voice control not working | Connected to internet and signed in? Yes; complete: Unpair, restart device, and re-pair; resolved? Yes | Correct success message appears, then the More Help prompt. | Correct success message appears, followed by the More Help prompt. | Pass | 21:23 | 0 | 2026-09-29
LB-030 | Core routing | Remote | Voice control not working | Connected to internet and signed in? Yes; complete: Unpair, restart device, and re-pair; resolved? No | Correct unresolved message appears and the support-request form opens. | Correct unresolved message appears followed by the support-request form opens. | Pass | 21:23 | 0 | 2026-09-29
LB-031 | Core routing | Remote | Voice control not working | Connected to internet and signed in? No; complete: Connect to Wi-Fi and sign in; resolved? Yes | Correct success message appears, then the More Help prompt. | Correct success message appears, followed by the More Help prompt. | Pass | 21:24 | 0 | 2026-09-29
LB-032 | Core routing | Remote | Voice control not working | Connected to internet and signed in? No; complete: Connect to Wi-Fi and sign in; resolved? No | Correct unresolved message appears and the support-request form opens. | Correct unresolved message appears followed by the support-request form opens. | Pass | 21:25 | 0 | 2026-09-29
LB-033 | Navigation | All categories | Main menu | Open a fresh published conversation | Four choices appear: Power, Connection, Audio/Video, and Remote. | All four choices appeared | Pass | 21:31 | 0 | 2026-09-29
LB-034 | Navigation | Success ending | More Help: Yes | Complete a success route and select Yes | Bot returns to the main menu and allows another issue selection. | Bot returns to the main menu | Pass | 21:32 | 0 | 2026-09-29
LB-035 | Navigation | Success ending | More Help: No | Complete a success route and select No | Bot displays the final closing message without restarting unexpectedly. | Closing message displayed | Pass | 21:33 | 0 | 2026-09-29
LB-036 | Form validation | Escalation | Required fields | Open the support-request form and submit it empty | Required fields prevent submission and identify what is missing. | It did not allow submission | Pass | 21:35 | 0 | 2026-09-29
LB-037 | Form validation | Escalation | Email validation | Enter an incorrectly formatted email address | The form rejects the invalid email and requests a valid format. | Invalid email was rejected | Pass | 21:37 | 0 | 2026-09-29
LB-038 | Personalization | Escalation | Saved fields | Submit valid sample name, email, device, issue, and permission | Confirmation displays the saved information and uses the person's name correctly. | Confirmation is displayed with the person's name | Pass | 21:38 | 0 | 2026-09-29
LB-039 | Form validation | Escalation | Contact permission | Test both Yes and No selections | Either permission choice saves correctly and does not break submission. | Confirmation displayed with both selectioins | Pass | 21:41 | 0 | 2026-09-29
LB-040 | Published experience | Fresh session | Published link and reset | Open the published link in a private/incognito window | The bot loads correctly and starts at the intended beginning. | Bot loads correctly and starts at the beginning | Pass | 21:43 | 0 | 2026-09-29

## Defect & Retest Log
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GEEK Streaming Support: Defect & Retest Log
Only add an entry when a Python, flowchart, or Landbot test reveals an issue. Document the correction and retest result so the progression is visible.
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Defects | Open / In Progress | Ready to Retest | Closed / Passed | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Defect ID | Related Test ID | Found In | Date Found | What Happened | Expected Behavior | Fix Applied | Retest Status | Date Retested | Evidence / Notes
DEF-001 | TC-034 and TC-039 | Python | 2026-09-28 | Input formatting was not normalized. Extra spaces caused the main-menu choice to be rejected, and uppercase YES followed the wrong diagnostic path. | Trim whitespace from menu selections and interpret yes/no responses regardless of capitalization. | Added .strip() to the main-menu input and created get_yes_no(), which applies .strip().lower() before validating the response. | Retest Passed | 2026-10-08 | TC-034 and TC-039 passed after the updated code was rerun in Google Colab.
DEF-002 | TC-040 | Python | 2026-09-28 | An invalid yes/no response such as “maybe” was treated as a successful resolution. | Reject responses other than yes or no and repeat the question until a valid answer is entered. | Used get_yes_no() with a validation loop that displays “Please enter yes or no.” and asks again. | Retest Passed | 2026-10-08 | TC-040 passed after Colab rejected the invalid response and prompted again for yes or no.